## SPRINT BACKLOG
SPRINT 1 BACKLOG
ID | User Story | Tasks | Owner | Status | Estimated effort | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
US001 | As a developer I want to be able to test the game in a 2d format | Create locomotion components bound to mouse and keyboard inputs | Tadhg Savage | Completed | 20 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Implement a way for vertical camera rotation to be registered by the mouse | Tadhg Savage | Completed |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Add a second set of ingame controllers with raycast functionality | Tadhg Savage | Completed |  | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US005 | As a player I want to be able to cook customers orders | Implement a system to list all types of food and create recipes to turn one or more types of food into another type of food | Tadhg Savage | Completed | 48 | 0 | 0 | 5 | 7 | 2 | 8 | 6 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0
|  | Implement an appliance to process food into other foods based on the recipes in the food list | Tadhg Savage | In Progress |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Add an additional socket to the socket prefab that detects any food that can be combined with the currently socketed food | Tadhg Savage | Completed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0
US011 | As a player I want to be able to move around. | Install and setup Unity's VR Interaction Toolkit package | Tadhg Savage | Completed | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0
|  | Add a locomotion object to the VR Rig | Tadhg Savage | Completed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 6 | 0 | 0
|  | Add a continuous movement provider to the locomition object | Tadhg Savage | Completed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0
|  | Add a continuous turn provider to the locomition object | Tadhg Savage | Completed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
[5 empty] | 78 | 0.5 | 8 | 11 | 9 | 2 | 8 | 6 | 6 | 7 | 3 | 2 | 8 | 6 | 4 | 8

## PROJECT DETAILS
PROJECT NUMBER | BSCH01_SE_02
PROJECT NAME | Cooktastrophe
PROJECT MANAGER | Tadhg Savage
DATE | 2023-04-19
VERSION | 1

## RESOURCES
Useful resources
Burndown Chart Template
Daily Scrum Meeting Template
Deployment Plan Template
Product Backlog Template
Project Management Templates