## PRODUCT BACKLOG
PRODUCT BACKLOG
User Story ID | User Story | Priority | Sprint
US001 | As a developer I want to be able to test the game in a 2D format. | High | 2
US002 | As a player, I want to be able to greet customers. | Medium | 4
US003 | As a player I want to be able to take customers' orders. | High | 4
US004 | As a player I want to be able to prepare and cook customers' orders. | High | 4
US006 | As a player I want to be able to leave a customers order for collection. | High | 4
US007 | As a player I want to be able to clear a customers table of its mess. | High | 4
US008 | As a player I want to be able to collect payment for the service. | Medium | 4
US009 | As a player I want to be able to clean dirty dishes left behind by customers. | High | 4
US010 | As a player I want to be able to use all appliances. | High | 3
US011 | As a player I want to be able to move around. | High | 1
US012 | As a player I want to be able to pick up and hold objects. | High | 1
US013 | As a player I want to be able to upgrade appliances. | Low | 6
US014 | As a player I want to be able to add cosmetics to my kitchen. | Low | 6
US015 | As a player I want the headset to consistently keep the correct orientation throughout gameplay. | High | 1
US016 | As a player I want clear, colourful graphics to be able to get the most visual enjoyment out the game. | High | 1
US017 | As a devloper I want a clear, concise testing plan to validate the application and verify that it is free of defects. | High | 6 | 0
Note on D8: stakeholdermap.com: Whatever method you are using for estimation. It could be story points, Fibonacci scale or T-shirt sizes - small, medium, large.
Note on E8: stakeholdermap.com: To change the Priority menu click on the DROPDOWN MENUS worksheet.
Note on F8: stakeholdermap.com: To change the Priority menu click on the DROPDOWN MENUS worksheet.
Note on G8: stakeholdermap.com: An optional field for the person responsible for the completion of the User Story.
Note on H8: stakeholdermap.com: This is an optional field for estimated effort in hours or days.

## PROJECT DETAILS
PROJECT NUMBER
PROJECT NAME
PROJECT MANAGER
DATE
VERSION

## DROPDOWN MENUS
PRIORITY | SPRINT
1 | 1
2 | 2
3 | 3
4 | 4
5 | 5
6
7
8
9
10
TO EDIT THE DROPDOWN MENUS
Click on the Data tab. Under Data Tools, select Data Validation. Under Settings change the Source to match the values you want to appear in the menu.
TO DELETE THE DROPDOWN MENUS
Click on the Data tab. Under Data Tools, select Data Validation. Under Settings change the Allow to Any value.

## RESOURCES
Useful resources
Burndown Chart Template
Daily Scrum Meeting Template
Project Management Templates
The Top 50 Business Risks (and how to manage them)!
Issue Log Template [free download]
End Project Report Template
Risk Register Template
Stakeholder Management Templates
Work Breakdown Structure (WBS) template in Excel